## Sheet1
Tasks | Semester 2, 2023 |  |  |  |  | Summer Break | Semester 1, 2024
| 8 | 9 | 10 | 11 | 12 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Phase 0 - Performing Pick-and-Place Tasks
Training Data Collection
Model Training
Performance Evaluation
Phase 1 - Learning Sorting Rules
Implementing Object Detection
Machine Learning for Behaviours
Phase 2 - Integration and Study 1
Integrating XR with the Robot
Study 1 - LfD using MRC
Phase 3 - UI Interventions and Study 2
Implementing UI Interventions | bar: Semester 1, 2024 1 to Semester 1, 2024 2
Study 2 - Impact of UI Interventions | bar: Semester 1, 2024 3 to Semester 1, 2024 5
Project Finalising
Final Thesis Writing